## Instructions
Class Planning Template
MDE-2_Class Plan.xls
Instructions
Description: | Another effective format for a project schedule is to use columns to denote
the week(s) before an event takes place so you can see all the tasks that
need to be completed 4 weeks before the event, 2 weeks before, 1 week
and so on.
I use this tool for every 5-day IT Manager Institute class I provide. It has
some valuable benefits:
1. Eliminates stress in preparing for a class because I can see
everything that's still outstanding. When every task has a
completed mark of "X", I know I'm ready.
2. Improves my productivity. What once took several hours of
"last minute" preparation is now done much faster.
3. Improves the quality of my class. Nothing is forgotten.
Use this tool for class preparation or other events you are putting together.
You will be pleased at what such a simple tool can do for you.
Instructions: | Step 1 | Fill in the event name and dates at the top.
| Step 2 | Put in the timeframes you want in the column headings. Add more if you
like. I use 4-weeks, 2-weeks, and 1-week before the event. I also
include a 1-week after the event to list follow-up items.
| Step 3 | List the tasks that must be completed to hold the event. I like to
group tasks into categories as you see in the template & example.
Add to or modify the tasks I've included in the template as you need.
| Step 4 | For each task, put a "/" (slash) in the appropriate column to signify
when the task should be completed.
| Step 5 | As tasks are completed, change the "/" to an "X" to signify task complete.
This makes the plan very visual and allows you to see where you are easily.

## Template
Location |  | Class Name
Institute Date: Date |  | To-Do
2010-05-25
Task | 4-wk | 2-wk | 1-wk | Week | +1-Week | Comments
Logistics:
Reserve classroom | /
Plane reservation | /
Auto reservation | /
Reserve my hotel room | /
Send prerequisite materials to students | /
Class materials preparation:
Update the slides |  | /
Print class Notebook & ship |  | /
Print class Tools Handout & ship |  | /
Print student Name Cards |  |  | /
Print class attendance certificates |  |  | /
Print class exam |  | /
Print class Survey forms |  |  | /
Giveaways:
Purchase Gift-1 | /
Purchase Gift-2 | /
Purchase Gift-3 | /
Create class CDs |  |  | /
Assemble Giveaways for class
- Gift-1 |  |  | /
- Gift-2 |  |  | /
- Gift-3 |  |  | /
- Institute CD's |  |  | /
Class materials:
Purchase flip chart pads |  |  | /
Check out projector |  |  | /
Check out Laptop - approp. class slides |  |  | /
Put accessories together:
- Power strip or extension cord |  |  |  | /
- Magic markers |  |  |  | /
- Flip chart stand |  |  |  | /
- Flip chart pad |  |  |  | /
- Camera (recharged) |  |  |  | /
- Class Master Slides on CD |  |  |  | /
- Extra projector lamp |  |  |  | /
- Extra paper pads & pens |  |  |  | /
Student preparation:
Review student prerequisite materials |  |  | /
Send students directions & class info. |  |  | /
Personal preparation:
Haircut |  |  | /
Cleaners |  |  | /
Bank |  |  | /
Clean car |  |  | /
Passport |  |  | /
Follow-up:
Action 1 |  |  |  |  | /
Action 2 |  |  |  |  | /
Action 3 |  |  |  |  | /

## Example
ARUBA |  | IT Manager Institute
Institute Date: Dec. 4-8, 2006 |  | To-Do
2006-11-29
Task | 4-wk | 2-wk | 1-wk | Week | +1-Week | Comments
Logistics:
Reserve classroom | X
Plane reservation | X
Auto reservation | X
Reserve my hotel room | X
Send prerequisite materials to students |  | X
Class materials preparation:
Update the slides |  | X
Print Institute Notebook & ship |  | X
Print Institute Tools Handout & ship |  | X
Print 30-Day Action Plan & ship |  | X
Print 30-Day Action Plan Sample & ship |  | X
Print IT Management Models & ship |  | X
Print Tent Cards |  |  | /
Print copies of IT Mgmt. Process |  | X
Print Institute certificates |  |  | /
Print ITBMC Exam |  | X
Giveaways:
Purchase IT-101 books (if needed) | X
Purchase briefcases | X
Purchase slver dollars | X
Create Institute CDs |  |  | X
Assemble Giveaways
- Briefcases |  |  | /
- IT Management-101 paperbacks |  |  | /
- Silver dollars |  |  | /
- Institute CD's |  |  | /
Class materials:
Purchase flip chart pads |  |  | na
Check out projector |  |  | na
Check out Laptop - approp. class slides |  |  | X
Put accessories together:
- Power strip or extension cord |  |  |  | na
- Magic markers |  |  |  | /
- Flip chart stand |  |  |  | na
- Flip chart pad |  |  |  | na
- Camera (recharged) |  |  |  | /
- Institute Master CD |  |  |  | /
- Extra projector lamp |  |  |  | na
- Extra paper pads & pens |  |  |  | na
Student preparation:
Review student prerequisite materials |  |  | X
Send directions |  |  | X
Personal preparation:
Haircut |  |  | X
Cleaners |  |  | /
Bank |  |  | /
Clean car |  |  | na
Passport |  |  | /
Follow-up
Send students follow-up email message |  |  |  |  | /
Add students to MDE Newsletter |  |  |  |  | /
Note:
This example is a real example of my preparation for a 5-day IT Manager Institute class being held in Aruba.
The time of the update was one week before the class so you see some tasks still left to be completed.
Because the class is hosted by a local company, there are some tasks that are not applicable as they would be
if I were hosting the class myself.